## YEAR 5 WORKPLAN
AFRICA CENTRE OF EXCELLENCE IN PUBLIC HEALTH AND HERBAL MEDICINE (ACEPHEM) | [9 empty] | Year 2022-2023
July 2021 - June 2022
Component | Sub- component | Action Plan | Objective | Justification | Output | DLI # | DLR # | Estimated Budget (US$) | Responsible Unit | July | August | September | October | November | December | January | February | March | April | May | June
1.0. ACE plan to achieve learning excellence | 1.1 Development of new carriculla or review of existing ones | 1 | Participatory review of curricula. Hold a regional consultative stakeholders workshop for curricula review. Revise existing curricula. Submit to UNIMA senate for approval. Submit the senate approved curricula to NCHE | Developed or Reviewed curricula to be Intenationally accredited | List of recommended areas for improvement. Revised curricula ready for UNIMA senate submission. Senate approved curricula. NCHE accredited curricula. | 2 | 2.4 | 223000 | ACEPHEM Leadership |  |  |  | X | X | X | X | X | X
| 1.2 Students recruited and supported | 1 | Markerting programs at ACEPHEM. Selection and admission of students.Offering small scale scholarship to studentsto attract female and regional students. Signed fellowship MOUs with partners | ACEPHEM students recruited and supported | National and regional students applications. Students admission list. Scholarships awarded. Fellowships MOUs | 2 | 2.3; 2.5 | 437117 | ACEPHEM Leadership | X | X | X |  |  |  | X | X | X
| 1.3 Rehabilitate and upgrade teaching and learning facilities | 1 | Upgrading teaching and learning facilities for academic excellence | Enabling environment for cutting edge learning and research | Improved teaching and learning facilities | 2 | 2.2 | 50000 | ACEPHEM & COM |  |  | X | X | X | X | X | X | X
| 1.4 Professional development and short courses | 1 | Develop a sustainable and ICT transferable curriculum for short courses/workshop | Professional development courses in pharmacovigillance and public health | Number of students, faculty, and industry leaders attending these workshops | 2 | 2.3 | 95000 | ACEPHEM Leadership |  |  | X | X | X | X | X | X | X | X
2.0. ACE action plan to achieve teaching and applied research excellence | 2.1 Procure general use teaching and research equipment and lab supplies | 2 | To procure general use teaching and research equipment and lab supplies | An improved research, conference and lab space | General teaching, research and lab supplies procured at ACEPHEM and partner institutions | 2 | 2.6 | 111600 | ACEPHEM Leadership | X | X | X | X | X | X | X | X | X | X | X
| 2.2 Core team to lead public health and herbal medicine research | 2 | Development of a core team to lead herbal medicine and public health research | Qualified individuals that will train students and faculty members on applied research | Retaining these trained personnel throughout the funding period | 2 | 2.2 | 101300 | ACEPHEM Leadership |  |  |  | X | X | X | X | X | X
| 2.3 Field site monitoring and support and vehicle maintenance | 2 | To maintain regular connections at all sites and maintain projects. | Vehicle used to collect herbal products and visiting collaborative partners | Number of monitoring visits conducted |  | 2.6 | 34600 | ACEPHEM Leadership and M&E |  |  | X | X | X | X | X | X | X | X | X
| 2.4 Facilitating international conference presentations and manuscript publication | 2 | Providing support for manuscript charges and conference attendance | attendance and manuscript published in peer reviewed journals | Number of students and faculty attending conferences. Number of publications | 2 | 2.5 | 16900 | ACEPHEM Leadership | [6 empty] | X | X | X | X | X | X
3.0. Attracting regional faculty and students | 3.1 Education outreach program | 3 | To conduct educational outreach program-providing international marketing to potential female students | Reaching out to females students and underserved communities |  | 2 | 2.5 | 7850 | ACEPHEM Leadership | [5 empty] | X | X | X | X | X | X | X
| 3.2 Facilitating national and regional student and faculty exchange program | 3 | Development of an exchange program for students and faculty members within malawian institutions as well as the region | Exchange program will R&D companies and sector organizations | Number of students, faculty members and interns exchanged | 2 | 2.6 | 32000 | ACEPHEM Leadership and M&E |  |  |  |  | X | X | X | X | X | X | X
| 3.3 Proposal development for possible funding (External revenue generation) | 3 | Developing proposals to generate external revenue |  | Number of succesful proposals | 2 |  | 22000 | ACEPHEM Leadership | [6 empty] | X | X | X | X | X | X
| Conduct short course in accordance to the need | 3 | To conduct a short course as part of generating external revenue |  | Number of people who attended the workshop | 2 |  | 20000 | ACEPHEM Leadership | [8 empty] | X
4.0 Collaboration with international partners | 4.1 International Academic Partners monitoring and support | 4 | To maintain sustainable partnerships and networks for research, development and training in herbal medicine and public health | Intensify sharing and research collaboration with International Academic Partners. | Enhanced quality and quantity of research in herbal medicine and public health | 2 | 2.6 | 34000 | ACEPHEM Leadership and M&E |  |  |  |  | X | X | X | X | X | X | X
| 4.2 MOU signing and joint Implementation Planning meeting | 4 | To maintain sustainable partnerships and networks for research, development and training in herbal medicine and public health |  | Number of MOUs signed | 4 | 4.1 | 51500 | ACEPHEM Leadership and Partner institutions
| 4.3 Partner implementation plan bi-Annual review meeting | 4 | To track the progress made by the partners with regards to the Joint implementation plan |  | Number of review meetings conducted | 4 | 4.2 | 8000 | ACEPHEM Leadership and Partner institutions | [5 empty] | X | [5 empty] | X
5.0. Plan for management and governance | 5.1 Project meetings conducted | 5 | To conduct management meetings, steering committee meetings, international advisory board meetings, Bi-annual and Annual review meetings | To have external input from steering committee members | Number of meetings conducted | 2 | 1.1; 3.2; 3.3 | 130866 | ACEPHEM Leadership | X | X | X | X | X | X | X | X | X | X | X | X
| 5.2 Capacity building of ACEPHEM Staff | 5 | To build the capacity of ACEPHEM staff in terms of various trainings with respect to needs assesment |  | Number of capacity building activities attended by ACEPHEM staff | 5 |  | 28000 | ACEPHEM Leadership and Staff |  |  |  | X | X | X | X | X | X | X | X | X
| 5.3 Administration offices furnished and equiped | 5 | To furnish and equip ACEPHEM administration offices | To create a conducive environment for ACEPHEM activities | Office equipment supplied | 2 | 1.5 | 8400 | ACEPHEM Leadership |  |  | X | X | X | X | X | X
TOTAL | [7 empty] | 1384133

## YEAR 5 DETAILED PLAN
ANNEX: DETAILED ACTIVITIES
ACTIVITY NAME | Quantity |  | Budget USD | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE
1.1 Existing curricula reviewed and improved | bar: JUL to JUNE
1.1.1 To hold a regional consultative stakeholder meeting for curriculum development or review (regional, international, and local partners)
1.1.2 Cost for accomodation | 25 | 180 | 4500
1.1.3 Visit by ACEPHEM leaders to 2 partner institutions | 4 | 3000 | 12000
1.1.4 Meals | 25 | 100 | 2500
1.1.5 Local transportation | 1 | 1500 | 1500
1.1.6 Resource person | 1 | 1500 | 1500
1.1.7 Workshop management | 1 | 1000 | 1000
1.1.8 Accreditation fees | 1 | 200000 | 200000
SUB-TOTAL |  |  | 223000
1.2 Students recruited and supported | bar: JUL to JUNE
1.2.1 Tuition support for PhD Students | 8 | 4000 | 32000
1.2.1.1 Tuition support for Masters Students | 34 | 3200 | 108800
1.2.2 Stipend support for Post Graduate students | 19 | 7200 | 136800
1.2.3. Internship Support | 5 | 750 | 3750
1.2.4 Internship research funds support | 5 | 533.4 | 2667
1.2.4 Masters research funds support | 5 | 10000 | 50000
1.2.4 Phd research funds support | 8 | 10000 | 80000
1.2.5 Recruitment of students costs | 1 | 2500 | 2500
1.2.8 Scholarship incentive: Regional PhD students each expected to publish 3 articles before graduating | 3 | 300 | 900
1.2.8 Scholarship incentive: National PhD students each expected to publish 3 articles before graduating | 16 | 300 | 4800
1.2.9 Regional Masters students each expected to publish at least one paper before graduating | 6 | 100 | 600
1.2.10 National Masters students each expected to publish at least one paper before graduating | 71 | 102.8169 | 7300
1.2.11 Communications with institutions and partners | 1 | 7000 | 7000
SUB TOTAL |  |  | 437117
1.3 Rehabilitate and upgrade teaching and learning facilities
1.3.1 Rehabiliatation of laboratories | 1 | 50000 | 50000 | bar: OCT to FEB
50000
1.4 Professional development and short courses for special groups | bar: JUL to JUNE
1.4.1 Training Needs assesment | 1 | 3000 | 3000
1.4.2 Refreshments | 10 | 1000 | 10000
1.4.3 Workshop management (Stationery) | 10 | 200 | 2000
1.4.4 Facilitators allowances | 10 | 3000 | 30000
1.4.5 Per Diems for participants (Partners) | 10 | 1000 | 10000
1.4.6 Accomodation | 10 | 2500 | 25000
1.4.7 Travel for non-national delegates | 4 | 1500 | 6000
1.4.8 Travel for national delegates | 6 | 1500 | 9000
SUB-TOTAL |  |  | 95000
2.1 Procure general use teaching and research equipment and lab supplies
2.1.1 Purchase of ICT equipment (Laptops, projectors and Accesories) | 5 | 1000 | 5000 | bar: SEP
2.1.2 Maintenance of heavy duty photocopier | 1 | 4000 | 4000 | bar: JUL
2.1.3 General Lab Equipment and supplies | 1 | 50000 | 50000 | bar: JUL to JUNE
2.1.4 Students travels and lodging to partner institutions | 5 | 2520 | 12600 | bar: SEP to DEC
2.1.5 Procurement of computer aided sperm analyzer | 1 | 40000 | 40000 | bar: OCT to DEC
SUB-TOTAL |  |  | 111600
2.2 Core team to lead public health and herbal medicine research | bar: JUL to JUNE
2.2.1 Salaries for ACEPHEM staff | 4 | 11200 | 44800
2.2.2 Development of Herbal Medicine research agenda | 1 | 26500 | 26500
1.2.3 Masters and PhD for Faculty | 1 | 30000 | 30000
SUB-TOTAL |  |  | 101300
2.3 Field site monitoring and support and vehicle maintenance | bar: JUL to JUNE
2.3.1 Vehicle maintenance and fuel | 2 | 5300 | 10600
2.3.2 Monitoring and supportive visits to partner institutions | 4 | 6000 | 24000
SUB-TOTAL |  |  | 34600
2.4 Facilitating international conference presentations and manuscript publication | bar: JUL to JUNE
2.4.1 Per Diems for participants (Partners) | 3 | 1000 | 3000
2.4.2 Travel costs | 3 | 1300 | 3900
2.4.3 Publication fees | 10 | 300 | 3000
2.4.4 Paying for international conferences | 10 | 200 | 2000
2.4.5 Research costs for staff | 5 | 1000 | 5000
SUB-TOTAL |  |  | 16900
3.1 Education outreach program | bar: JUL to JUNE
3.1.1 Maintenance of ACEPHEM website | 1 | 2000 | 2000
3.1.2 High School Science Teachers training | 5 | 530 | 2650
3.1.3 Open day | 1 | 1200 | 1200
3.1.4 Community Outreach | 1 | 2000 | 2000
SUB-TOTAL |  |  | 7850
3.2 Facilitating national and regional student and faculty exchange program | bar: JUL to JUNE
3.2.1 Accomodation | 8 | 2500 | 20000
3.2.2 Travel costs | 8 | 1500 | 12000
SUB-TOTAL |  |  | 32000
3.3 Proposal development for possible funding (External revenue generation)
3.3.1 Allowances | 20 | 500 | 10000
3.3.2 Conference Package | 3 | 2500 | 7500
3.3.3 Travel Cost for Local Partners | 3 | 1500 | 4500
SUB TOTAL |  |  | 22000
3.4 Conduct short courses (as part of external revenue generation) | 2 | 10000 | 20000 | bar: JUL to JUNE
4.1 International Academic Partners monitoring and support | bar: JUL to JUNE
4.1.1 Travel | 4 | 1500 | 6000
4.1.2 Accomodation | 4 | 2000 | 8000
4.1.4 Meetings with partners | 4 | 2500 | 10000
4.1.5 Grant writing meetings with partner institutions | 4 | 2500 | 10000
SUB-TOTAL |  |  | 34000
4.2 MOU signing and joint Implementation Planning meeting
4.2.1 Conference Package | 2 | 4000 | 8000
4.2.2 Per diem for local partners | 3 | 500 | 1500
4.2.3 Refreshments | 10 | 200 | 2000
4.2.5 Travel cost and perdiems (International) | 10 | 4000 | 40000
SUB TOTAL |  |  | 51500
4.3 Partner implementation plan bi-Annual review meeting | bar: JUL to JUNE
4.3.1 Conference Package | 1 | 4000 | 4000
4.3.2 Per diem for local partners | 3 | 500 | 1500
4.3.3 Refreshments | 1 | 1000 | 1000
4.3.5 Travel cost for local Partners | 10 | 150 | 1500
SUB TOTAL |  |  | 8000
5.1 Project meetings conducted | bar: JUL to JUNE
5.2.1 Accomodation for ISAB meeting | 2 | 13333 | 26666
5.2.1 Per diems for ISAB meeting | 2 | 3200 | 6400
5.2.3 Visa cost | 2 | 1400 | 2800
5.2.4 Local travel | 2 | 1500 | 3000
5.2.5 Conference package | 2 | 4000 | 8000
5.2.6 Travel Cost (International) | 2 | 15000 | 30000
5.2.7 Accomodation for National Steering meeting | 10 | 400 | 4000
5.2.8 Travel for National Steering meeting | 10 | 300 | 3000
5.2.9 Conference Package | 1 | 1000 | 1000
5.3.1 Per diem for local steering committee meeting | 5 | 400 | 2000
5.3.2 Refreshments for local steering committee meeting | 1 | 400 | 400
5.3.3 Per diem for local steering committee meeting |  |  | 0
5.3.4 Travel cost for local steering committee meeting | 8 | 600 | 4800
0
5.2.8 Per diem for sub-committee meeting | 5 | 400 | 2000
5.2.7 Per diem for sub-committee meeting |  |  | 0
5.2.9 Refreshments for sub-committee meeting | 1 | 400 | 400
5.3.0 Travel cost for sub-committee meeting | 4 | 600 | 2400
5.3.1 ACEPHEM members travel cost | 4 | 1500 | 6000
5.3.2 Capacity Building Workshops for ACEPHEM Staff | 4 | 7000 | 28000
SUB-TOTAL |  |  | 130866
5.3 Administration offices funished and equiped | bar: JUL to JUNE
5.3.1 Office furniture | 1 | 3000 | 3000
5.3.2 Communication | 12 | 250 | 3000
5.3.3 General Office supplies | 12 | 200 | 2400
8400
GRAND TOTAL |  |  | 1384133

## Progress to date
AFRICA CENTRE OF EXCELLENCE IN PUBLIC HEALTH AND HERBAL MEDICINE (ACEPHEM)
Component | Sub- component | Objective | Justification | Output | Progress to date
1.0. ACE plan to achieve learning excellence | 1.1 Development of new carriculla or review of existing ones | Participatory review of curricula. Hold a regional consultative stakeholders workshop for curricula review. Revise existing curricula. Submit to UNIMA senate for approval. Submit the senate approved curricula to NCHE | Developed or Reviewed curricula to be Intenationally accredited | List of recommended areas for improvement. Revised curricula ready for UNIMA senate submission. Senate approved curricula. NCHE accredited curricula.
| 1.2 Students recruited and supported | Markerting programs at ACEPHEM. Selection and admission of students.Offering small scale scholarship to studentsto attract female and regional students. Signed fellowship MOUs with partners | ACEPHEM students recruited and supported | National and regional students applications. Students admission list. Scholarships awarded. Fellowships MOUs | Advertisement for the programs at ACEPHEM was done. We are currently processing the applications. The recruitment to be done early next year
| 1.3 Rehabilitate and upgrade teaching and learning facilities | Upgrading teaching and learning facilities for academic excellence | Enabling environment for cutting edge learning and research | Improved teaching and learning facilities | The project is assisting the University in buildinga perimeter fence around the institutional houses which also houses international students.
| 1.4 Professional development and short courses | Develop a sustainable and ICT transferable curriculum for short courses/workshop | Professional development courses in pharmacovigillance and public health | Number of students, faculty, and industry leaders attending these workshops | We have conducted a total of xx short courses. The short courses were in these areas: Manuscript wriring, grant writing. A total of xx students, xxx faculty and xxx industrial leaders attended the workshops.
2.0. ACE action plan to achieve teaching and applied research excellence | 2.1 Procure general use teaching and research equipment and lab supplies | To procure general use teaching and research equipment and lab supplies | An improved research, conference and lab space | General teaching, research and lab supplies procured at ACEPHEM and partner institutions
| 2.2 Core team to lead public health and herbal medicine research | Development of a core team to lead herbal medicine and public health research | Qualified individuals that will train students and faculty members on applied research | Retaining these trained personnel throughout the funding period | This is ongoing
| 2.3 Field site monitoring and support and vehicle maintenance | To maintain regular connections at all sites and maintain projects. | Vehicle used to collect herbal products and visiting collaborative partners | Number of monitoring visits conducted
| 2.4 Facilitating international conference presentations and manuscript publication | Providing support for manuscript charges and conference attendance | attendance and manuscript published in peer reviewed journals | Number of students and faculty attending conferences. Number of publications | Supported students in peer reviewed journals. Supported the University in hosting a COVID conference online.
3.0. Attracting regional faculty and students | 3.1 Education outreach program | To conduct educational outreach program-providing international marketing to potential female students | Reaching out to females students and underserved communities
| 3.2 Facilitating national and regional student and faculty exchange program | Development of an exchange program for students and faculty members within malawian institutions as well as the region | Exchange program will R&D companies and sector organizations | Number of students, faculty members and interns exchanged | The project hosted faculty from University of Zambia for two weeks on an exchange programme. A total of xx faculty members participated
| 3.3 Proposal development for possible funding (External revenue generation) | Developing proposals to generate external revenue |  | Number of succesful proposals | The project has completed and submitted 6 proposals. The proposals have been submitted to :
| Conduct short course in accordance to the need | To conduct a short course as part of generating external revenue |  | Number of people who attended the workshop
4.0 Collaboration with international partners | 4.1 International Academic Partners monitoring and support | To maintain sustainable partnerships and networks for research, development and training in herbal medicine and public health | Intensify sharing and research collaboration with International Academic Partners. | Enhanced quality and quantity of research in herbal medicine and public health
| 4.2 MOU signing and joint Implementation Planning meeting | To maintain sustainable partnerships and networks for research, development and training in herbal medicine and public health |  | Number of MOUs signed | The university signed an MOU with University of Huddlesfield in UK focusing on student exchange.
| 4.3 Partner implementation plan bi-Annual review meeting | To track the progress made by the partners with regards to the Joint implementation plan |  | Number of review meetings conducted | The project review meeting is planned for December 2021
5.0. Plan for management and governance | 5.1 Project meetings conducted | To conduct management meetings, steering committee meetings, international advisory board meetings, Bi-annual and Annual review meetings | To have external input from steering committee members | Number of meetings conducted | The project has held 1 (One) Project Risk and Audit Sub committee meeting and 1 (One) Project Steering Committee Meeting. The National Sttering Committee Meeting will be held on 1st December 2021
| 5.2 Capacity building of ACEPHEM Staff | To build the capacity of ACEPHEM staff in terms of various trainings with respect to needs assesment |  | Number of capacity building activities attended by ACEPHEM staff
| 5.3 Administration offices furnished and equiped | To furnish and equip ACEPHEM administration offices | To create a conducive environment for ACEPHEM activities | Office equipment supplied | Ongoing
TOTAL