## Sources and Uses of Funds
COLLEGE OF MEDICINE (UNIVERSITY OF MALAWI)
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT (151847)
Statement of Sources and Uses of Funds
for the semi-annual period ending 30 June 2022
Cummulative for
Sources of Fund | Financial Year End Dec 31 2021 | Period ending June 2022
| USD | USD
Opening Cash Balance
Government Funds
World Bank IDA Funds | 396784.7668 | 477628.144
Student Fees
Others | 26386.7686 | 37149.7666
Total | 423171.5355 | 514777.9106
Add Receipts
Government Funds
World Bank IDA Funds | 399685 | 0
Student Fees
Others | 49511.67 | 127773.2922
Total Financing | 872368.2055 | 642551.2028
Less: ACE Expenditure as per Project Implementation Plan
1.1 Existing curricula reviewed and improved | 2002.7165 | 424.0648
1.2 Students recruited and supported | 91142.9806 | 10259.6995
1.3 Rehabilitate and upgrade teaching and learning facilities | 2877.0722 | 3971.2519
1.4 Professional development and short courses for special groups | 11920.9301 | 1005
2.1 Procure general use teaching and research equipment and lab supplies | 1308.0969 | 15051.0826
2.2 Core team to lead public health and herbal medicine research | 64531.0068 | 63210.4072
2.3 Field site monitoring and support and vehicle maintenance | 7369.1404 | 10206.704
2.4 Facilitating international conference presentations and manuscript publication | 46408.6098 | 29014.4954
3.1 Education outreach program | 2909.0993 | 10647.5698
3.2 Facilitating national and regional student and faculty exchange program | 9334.1365 | 12101
3.3 Proposal development for possible funding (External revenue generation) | 51389.57 | 42696.8275
3.4 Conduct short courses (as part of external revenue generation) | 18894 | 23531.8978
4.1 International Academic Partners monitoring and support | 7789 | 1542
4.2 MOU signing and joint Implementation Planning meeting | 1752 | 638.0245
4.3 Partner implementation plan bi-Annual review meeting | 4791 | 454.3253
5.1 Project meetings conducted | 21803.7968 | 1241
5.3 Administration offices funished and equiped | 11367.1341 | 1317
Total Uses of Funds by Components | 357590.2899 | 227312.3504 | 584902.6391
Closing Balances | 514777.9155 | 415238.8524 | 0.0012052
Government Funds
World Bank IDA Funds | 477628.144 | 340451.7218
Student Fees
Others | 37149.7666 | 74787.1318
Total Closing Cash Balance | 514777.9106 | 415238.8536
-0.0011988

## Uses of Funds as per PIM
College of Medicine
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT
Uses of Funds (Breakdown)
for the semi-annual period ending…30 June 2022
Expenditure | Cummulative for |  |  |  | Period ending June 2022 |  | Explanation of | PAD /Life of | Revised
|  | Financial Year Ending Dec 2021 |  |  |  |  | Variance | Project | PAD
| Actual US$ | Planned US$ | Variance US$ | Actual US$ | Planned US$ | Variance US$
Expenditure Classification 1 as per Project Implementation Plan
1.1 Existing curricula reviewed and improved | 4545 | 211196.2032 | 206651.2032 | 4969.0648 | 223000 | 218030.9352 | Work is in progress as stakeholders need more time
1.2 Students recruited and supported | 525229.3838 | 487474.0194 | -37755.3644 | 10259.6995 | 578617 | 568357.3005 | In Progress
1.3 Rehabilitate and upgrade teaching and learning facilities | 42307.0373 | 36380 | -5927.0373 | 3971.2519 | 300000 | 296028.7481 | Done
1.4 Professional development and short courses for special groups | 4758.3316 | 89778.2606 | 85019.929 | 1005 | 95000 | 93995 | Work is in progress as stakeholders need more time
2.1 Procure general use teaching and research equipment and lab supplies | 25673.0565 | 45279.7402 | 19606.6836 | 15051.0826 | 85600 | 70548.9174 | Partly procured Equipment more in progress
2.2 Core team to lead public health and herbal medicine research | 27479.5495 | 74820.0632 | 47340.5137 | 63210.4072 | 101300 | 38089.5928 | Work is in progress as stakeholders need more time
2.3 Field site monitoring and support and vehicle maintenance | 5428.434 | 32581.8416 | 27153.4077 | 10206.704 | 34600 | 24393.296 | Cars relatively new hence maintenance costs low
2.4 Facilitating international conference presentations and manuscript publication | 38185.3654 | 15461.3604 | -22724.005 | 29014.4954 | 16900 | -12114.4954 | Work is in progress as stakeholders need more time
3.1 Education outreach program | 6795 | 6940.9007 | 145.9007 | 10647.5698 | 7850 | -2797.5698 | In Progress
3.2 Facilitating national and regional student and faculty exchange program | 2540 | 28858.1872 | 26318.1872 | 12101 | 32000 | 19899 | In Progress
3.3 Proposal development fopr possible funding (External revenue generation) | 60220.0787 | 29389.57 | -30830.5087 | 42696.8275 | 22000 | -20696.8275 | In Progress
3.4 Conduct short courses (as part of external revenue generation) | 8941 | 18106 | 9165 | 23531.8978 | 20000 | -3531.8978 | Work is in progress as stakeholders need more time
4.1 International Academic Partners monitoring and support | 1547 | 33211 | 31664 | 1542 | 34000 | 32458 | Work is in progress as stakeholders need more time
4.2 MOU signing and joint Implementation Planning meeting | 1542 | 50748 | 49206 | 638.0245 | 51500 | 50861.9755 | Work is in progress as stakeholders need more time
4.3 Partner implementation plan bi-Annual review meeting | 17951 | 7209 | -10742 | 454.3253 | 8000 | 7545.6747 | In Progress
5.1 Project meetings conducted | 33190.5325 | 145796.2032 | 112605.6707 | 1241 | 157600 | 156359 | Work is in progress as stakeholders need more time
5.3 Administration offices funished and equiped | 31796.1912 | 7032.8659 | -24763.3253 | 1317 | 8400 | 7083 | In Progress
0
| 838128.9605 | 1320263.2157 | 482134.2552 | 231857.3504 | 1776367 | 1544509.6496

## EEP Statement
COLLEGE OF MEDICINE (UNIVERSITY OF MALAWI)
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT (151847))
Statement of Reimbursable Eligible Expenditure Programs (EEPs)
for the period ending 30 June 2022
817.3026
Cummulative for
Eligible Expenditure Program (EEP) | Semi-Annual Period ending December 2021 MK | Semi-Annual Period ending December 2021 US$ | Financial Year End June 30, 2022 MK | Financial Year End June 30, 2022 US$
EEP 1: Salaries | 4476160366.22 | 5800150.2157 | 9167858838.29 | 11217214.8214
EEP 2: Teaching and laboratory materials | 21273052.5 | 27565.3439 | 63716219.21 | 77959.1539
EEP 3: Printing and stationery | 79314467.03 | 102774.6518 | 221595410.21 | 271130.1912
EEP 4: Communation expenses | 326201879.83 | 422688.1409 | 548684968.93 | 671336.3801
EEP 5: Student provisions | 3684516.05 | 4774.3478 | 4844730.34 | 5927.707
EEP 6: Fuels and oils | 59662008.5 | 77309.2524 | 129575093.08 | 158539.9252
EEP 7: Utilities | 288768338.23 | 374182.246 | 597228755.59 | 730731.5009
EEP 8: Insurance | 98584668.44 | 127744.7274 | 116371259.14 | 142384.5454
EEP 9: Maintenance expenses | 254562103.15 | 329858.2528 | 477516341.6 | 584258.9288
EEP 10: Training and staff development | 130568907.16 | 169189.4868 | 153340686.88 | 187618.0094
Total EEPs | 5738780307.11 | 7436236.6655 | 11480732303.27 | 14047101.1634

## DLI Statement
COLLEGE OF MEDICINE (UNIVERSITY OF MALAWI)
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT (151847)
NOTES ANNEX
DISBURSEMENT LINKED TO INDICATORS | ACTIONS TO BE COMPLETED | STATUS OF ACTIONS COMPLETION | AMOUNT ALLOCATED | AMOUNT DISBURSED | UNDISBURSED BALANCE
DLR 1.1 Signing of the performance and funding agreements and establishing national steering committee | Completion of effectiveness conditions | Done | 600000 | 600000 | 0
DLR 1.2 Development of the project implementation plan | Detailed implemetation plans for ACE approved by ministry in charge of higher education | Done | 500000 | 500000 | 0
DLR 2.1 Timely implementation of annual work plans | Timely execution of annual work plan | 60% completed | 0 | 0 | 0
DLR 2.2 Newly enrolled students in the ACE of which at least 20% must be regional African students | Enrol 126MSc and 10PhD students | Enrolled 140 MSc and 18 PhD students | 1300000 | 560350.03 | 739649.97
DLR 2.3 Quality accrediatation for education programs | Accreditation at National level submitted to NCHE | All 5 programs not yet accredited | 600000 | 300000 | 300000
DLR 2.4 partnership for collaboration in applied research and training | To sign 6 MoUs | Signed 10 MoUs | 200000 | 200000 | 0
DLR 2.5 peer reviewed journal papers or peer reviewed conference papers prepared collaboratively with national, regional or international co authors | Publish 5 papers | 4 papers published and others in different stages of publication | 500000 | 500000 | 0
DLR 2.6 faculty and PHD student exchanges to promote regional research and teraching collaborations | 8 national, 24 regional and 8 international faculty exchanged | 7 faculty, 1 PhD and 2 Technical staff sent, whilst 3 came to COM (1 national and 2 international), awaiting 10 staff from RUFORUM universities | 700000 | 66000 | 634000
DLR 2.7 External revenue generation | Generate $900,000 | $455,000 generated | 900000 | 900000 | 0
DLR 2.8 institution participating in benchmarking exercise | To enroll for benchmarking under PASET this year 2018 | Waiting for opening by PASET | 100000 | 100000 | 0
DLR 3.1 Timely withdrawal applications supported by interim unaudited financial reports | Internal audit committee produces unaudited financial report | Interim unaudited financial report almost through | 75000 | 60000 | 15000
DLR 3.2 Functioning audit committee | Formation of Internal audit committee and minutes available | In place | 75000 | 30000 | 45000
DLR 3.3 Functioning internal audit unit | Formation of Internal audit committee and minutes available | In place | 75000 | 30000 | 45000
DLR 3.4 Transparency of financial management | Setting up financial management dissemination channels | Financial report is ready, shared through website | 75000 | 30000 | 45000
DLR 4.1 timely procurement audit reports | Produce procurement report together with finacial report | Procurement report available with financial report | 150000 | 90000 | 60000
DLR 4.2timely and satisfactory procurement progress report | Postings done on WB site | Completed and in progress for subsequent reports. | 150000 | 90000 | 60000
|  |  | 6000000 | 4056350.03 | 1943649.97
0.67606

## AWP
ANNEX: DETAILED ACTIVITIES
ACTIVITY NAME | Quantity |  | Budget USD | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE
1.1 Existing curricula reviewed and improved | bar: JUL to JUNE
1.1.1 To hold a regional consultative stakeholder meeting for curriculum development or review (regional, international, and local partners)
1.1.2 Cost for accomodation | 25 | 180 | 4500
1.1.3 Visit by ACEPHEM leaders to 2 partner institutions | 4 | 3000 | 12000
1.1.4 Meals | 25 | 100 | 2500
1.1.5 Local transportation | 1 | 1500 | 1500
1.1.6 Resource person | 1 | 1500 | 1500
1.1.7 Workshop management | 1 | 1000 | 1000
1.1.8 Accreditation fees | 1 | 200000 | 200000
SUB-TOTAL |  |  | 223000
1.2 Students recruited and supported | bar: JUL to JUNE
1.2.1 Tuition support for PhD Students | 11 | 10000 | 110000
1.2.1.1 Tuition support for Masters Students | 34 | 3200 | 108800
1.2.2 Stipend support for Post Graduate students | 19 | 7200 | 136800
1.2.3. Internship Support | 5 | 750 | 3750
1.2.4 Internship research funds support | 5 | 533.4 | 2667
1.2.4 Masters research funds support | 15 | 10000 | 150000
1.2.4 Phd research funds support | 4 | 10000 | 40000
1.2.5 Recruitment of students costs | 1 | 6000 | 6000
1.2.8 Scholarship incentive: Regional PhD students each expected to publish 3 articles before graduating | 3 | 300 | 900
1.2.8 Scholarship incentive: National PhD students each expected to publish 3 articles before graduating | 16 | 300 | 4800
1.2.9 Regional Masters students each expected to publish at least one paper before graduating | 6 | 100 | 600
1.2.10 National Masters students each expected to publish at least one paper before graduating | 71 | 102.8169 | 7300
1.2.11 Communications with institutions and partners | 1 | 7000 | 7000
SUB TOTAL |  |  | 578617
1.3 Rehabilitate and upgrade teaching and learning facilities
1.3.1 Purchasing of ODL premises | 1 | 300000 | 300000 | bar: OCT to FEB
300000
1.4 Professional development and short courses for special groups | bar: JUL to JUNE
1.4.1 Training Needs assesment | 1 | 3000 | 3000
1.4.2 Refreshments | 10 | 1000 | 10000
1.4.3 Workshop management (Stationery) | 10 | 200 | 2000
1.4.4 Facilitators allowances | 10 | 3000 | 30000
1.4.5 Per Diems for participants (Partners) | 10 | 1000 | 10000
1.4.6 Accomodation | 10 | 2500 | 25000
1.4.7 Travel for non-national delegates | 4 | 1500 | 6000
1.4.8 Travel for national delegates | 6 | 1500 | 9000
SUB-TOTAL |  |  | 95000
2.1 Procure general use teaching and research equipment and lab supplies
2.1.1 Purchase of ICT equipment (Laptops, projectors and Accesories) | 15 | 1000 | 15000 | bar: SEP
2.1.2 Maintenance of heavy duty photocopier | 1 | 8000 | 8000 | bar: JUL
2.1.3 General Lab Equipment and supplies | 1 | 50000 | 50000 | bar: JUL to JUNE
2.1.4 Students travels and lodging to partner institutions | 5 | 2520 | 12600 | bar: SEP to DEC
SUB-TOTAL |  |  | 85600
2.2 Core team to lead public health and herbal medicine research | bar: JUL to JUNE
2.2.1 Salaries for ACEPHEM staff | 4 | 11200 | 44800
2.2.2 Development of Herbal Medicine research agenda | 1 | 26500 | 26500
1.2.3 Masters and PhD for Faculty | 1 | 30000 | 30000
SUB-TOTAL |  |  | 101300
2.3 Field site monitoring and support and vehicle maintenance | bar: JUL to JUNE
2.3.1 Vehicle maintenance and fuel | 2 | 5300 | 10600
2.3.2 Monitoring and supportive visits to partner institutions | 4 | 6000 | 24000
SUB-TOTAL |  |  | 34600
2.4 Facilitating international conference presentations and manuscript publication | bar: JUL to JUNE
2.4.1 Per Diems for participants (Partners) | 3 | 1000 | 3000
2.4.2 Travel costs | 3 | 1300 | 3900
2.4.3 Publication fees | 10 | 300 | 3000
2.4.4 Paying for international conferences | 10 | 200 | 2000
2.4.5 Research costs for staff | 5 | 1000 | 5000
SUB-TOTAL |  |  | 16900
3.1 Education outreach program | bar: JUL to JUNE
3.1.1 Maintenance of ACEPHEM website | 1 | 2000 | 2000
3.1.2 High School Science Teachers training | 5 | 530 | 2650
3.1.3 Open day | 1 | 1200 | 1200
3.1.4 Community Outreach | 1 | 2000 | 2000
SUB-TOTAL |  |  | 7850
3.2 Facilitating national and regional student and faculty exchange program | bar: JUL to JUNE
3.2.1 Accomodation | 8 | 2500 | 20000
3.2.2 Travel costs | 8 | 1500 | 12000
SUB-TOTAL |  |  | 32000
3.3 Proposal development for possible funding (External revenue generation)
3.3.1 Allowances | 20 | 500 | 10000
3.3.2 Conference Package | 3 | 2500 | 7500
3.3.3 Travel Cost for Local Partners | 3 | 1500 | 4500
SUB TOTAL |  |  | 22000
3.4 Conduct short courses (as part of external revenue generation) | 2 | 10000 | 20000 | bar: JUL to JUNE
4.1 International Academic Partners monitoring and support | bar: JUL to JUNE
4.1.1 Travel | 4 | 1500 | 6000
4.1.2 Accomodation | 4 | 2000 | 8000
4.1.4 Meetings with partners | 4 | 2500 | 10000
4.1.5 Grant writing meetings with partner institutions | 4 | 2500 | 10000
SUB-TOTAL |  |  | 34000
4.2 MOU signing and joint Implementation Planning meeting
4.2.1 Conference Package | 2 | 4000 | 8000
4.2.2 Per diem for local partners | 3 | 500 | 1500
4.2.3 Refreshments | 10 | 200 | 2000
4.2.5 Travel cost and perdiems (International) | 10 | 4000 | 40000
SUB TOTAL |  |  | 51500
4.3 Partner implementation plan bi-Annual review meeting | bar: JUL to JUNE
4.3.1 Conference Package | 1 | 4000 | 4000
4.3.2 Per diem for local partners | 3 | 500 | 1500
4.3.3 Refreshments | 1 | 1000 | 1000
4.3.5 Travel cost for local Partners | 10 | 150 | 1500
SUB TOTAL |  |  | 8000
5.1 Project meetings conducted | bar: JUL to JUNE
5.2.1 Accomodation for ISAB meeting | 2 | 13333 | 26666
5.2.1 Per diems for ISAB meeting | 2 | 3200 | 6400
5.2.3 Visa cost | 2 | 1400 | 2800
5.2.4 Local travel | 2 | 1500 | 3000
5.2.5 Conference package | 2 | 4000 | 8000
5.2.6 Travel Cost (International) | 2 | 15000 | 30000
5.2.7 Accomodation for National Steering meeting | 10 | 400 | 4000
5.2.8 Travel for National Steering meeting | 10 | 300 | 3000
5.2.9 Conference Package | 1 | 1000 | 1000
5.3.1 Per diem for local steering committee meeting | 5 | 400 | 2000
5.3.2 Refreshments for local steering committee meeting | 1 | 400 | 400
5.3.3 Per diem for local steering committee meeting |  |  | 26734
5.3.4 Travel cost for local steering committee meeting | 8 | 600 | 4800
0
5.2.8 Per diem for sub-committee meeting | 5 | 400 | 2000
5.2.7 Per diem for sub-committee meeting |  |  | 0
5.2.9 Refreshments for sub-committee meeting | 1 | 400 | 400
5.3.0 Travel cost for sub-committee meeting | 4 | 600 | 2400
5.3.1 ACEPHEM members travel cost | 4 | 1500 | 6000
5.3.2 Capacity Building Workshops for ACEPHEM Staff | 4 | 7000 | 28000
SUB-TOTAL |  |  | 157600
5.3 Administration offices funished and equiped | bar: JUL to JUNE
5.3.1 Office furniture | 1 | 3000 | 3000
5.3.2 Communication | 12 | 250 | 3000
5.3.3 General Office supplies | 12 | 200 | 2400
8400
GRAND TOTAL |  |  | 1776367
0

## June 2022 TB & Financials
Account Number | Description | Debits | Credits | 817.3026 | Debits | Credits
|  | MKW | MKW |  | USD | USD
1000-165-5 | Grants received : ACE PHEM | 0 | 304885993.05 |  |  | 373039.304
1400-165-5 | Interest received : ACE PHEM | 0 | 909324.58 |  |  | 1112.5923
1900-165-5 | Other Income : ACE PHEM | 0 | 77283532.21 |  |  | 94559.2639
1920-165-5 | Exchange Gain: ACEPHEM | 0 | 26236587.15 | 409315436.99 |  | 32101.4361 | 500812.5962
2000-165-5 | Staff costs : - ACEPHEM | 104403389.76 | 0 |  | 127741.414
2016-165-5 | Consultant : -Acephem Project | 9199760.81 | 0 |  | 11256.2481
2500-165-5 | Stationery and Printing costs : ACE PHEM | 1532326 | 0 |  | 1874.8576
2605-165-5 | Lab Supplies : ACE PHEM | 1129500 | 0 |  | 1381.9851
2801-165-5 | Advertisements : ACE PHEM | 595204.32 | 0 |  | 728.2545
3652-165-5 | Meeting Expenses : -ACEPHEM | 116399719.38 | 0 |  | 142419.3675
3701-165-5 | Fuel : - ACEPHEM | 12850283.33 | 0 |  | 15722.7976
3702-165-5 | Subsistene allowance : ACE PHEM | 61643500 | 0 |  | 75423.1052
3703-165-5 | Accomodation and Meals : - ACEPHEM | 68520 | 0 |  | 83.8368
3706-165-5 | Vehicle Hiring : ACEPHEM | 1514500 | 0 |  | 1853.0468
3708-165-5 | Workshops / Meetings : ACE PHEM | 10519565.36 | 0 |  | 12871.0778
3800-165-5 | External travel : ACE PHEM | 1358168.94 | 0 |  | 1661.77
3801-165-5 | Cost of Airticket : ACE PHEM | 45912850 | 0 |  | 56176.0724
3851-165-5 | Communication : ACE PHEM | 3350000 | 0 |  | 4098.8491
3900-165-5 | Maintainance of Motor vehicle : ACE PHEM | 3157517.97 | 0 |  | 3863.3402
4301-165-5 | Fellowship Programmes : ACE PHEM | 82876674.06 | 0 |  | 101402.6801
4600-165-5 | General expenses : - ACEPHEM | 5597153.1 | 0 |  | 6848.3241
4609-165-5 | Exchange Loss: ACEPHEM | 930331.2 | 0 |  | 1138.2947
4610-165-5 | Bank Charges : ACE PHEM | 1053083.47 | 0 |  | 1288.4866
4925-165-5 | Special Expense-Computers : - ACE PHEM | 13370400 | 0 |  | 16359.1796
4930-165-5 | Special Expense-Furniture and Fittings : ACE PHEM | 580000 | 0 | 478042447.7 | 709.6515 |  | 584902.6391
5010-165-5 | Lands & Buildings : ACEPHEM | 473955333 | 0 |  | 579901.9029
5200-165-5 | Office equipment : -ACEPHEM | 28710241.38 | 0 |  | 35128.0436
5210-165-5 | Computers - ACEPHEM | 15399750.12 | 0 |  | 18842.1646
5220-165-5 | Laboratory & Hospital Equipment: ACEPHEM | 11829000 | 0 |  | 14473.2196
5300-165-5 | Furniture and fittings : ACEPHEM | 5767375 | 0 |  | 7056.5969
5400-165-5 | Motor vehicles : ACEPHEM | 132567437.31 | 0 |  | 162201.1692
5500-165-5 | Accumm Depn - Land & Buildings : ACEPHEM | 0 | 35955146.43 |  |  | 43992.4533
5502-165-5 | Accumm Depn - Furniture & Fittings :ACEPHEM | 0 | 4168866.25 |  |  | 5100.7623
5503-165-5 | Accumm Depn - Motor Vehicles :ACEPHEM | 0 | 93431445.25 |  |  | 114316.8335
5506-165-5 | Accumm Depn - Office Equipment : ACEPHEM | 0 | 20709752.12 |  |  | 25339.1487
5507-165-5 | Accumm Depn - Computers : ACEPHEM | 0 | 15700735.06 |  |  | 19210.4308
5509-165-5 | Accumm Depn - Laboratory & Hospital Equipment - ACEPHEM | 0 | 8871750 |  |  | 10854.9147
6000-165-5 | Debtors Transactions : ACE PHEM | 1073719.32 | 0 |  | 1313.7354
6438-165-5 | African Centre for Public Health and Herbal Medicine FCDA | 256631022.18 | 0 |  | 313997.56
6439-165-5 | African Centre for Public Health and Herbal Medicine Local | 21621055.23 | 0 |  | 26454.1618
6800-165-5 | Cash Imprest - ACE PHEM Cash Imprest | 6309009.76 | 0 |  | 7719.3071
7201-165-5 | Withholding Tax Control Account : ACE PHEM | 0 | 14691371.14 |  |  | 17975.4367
7204-165-5 | VAT Control Account : ACE PHEM | 0 | 709840.58 |  |  | 868.5162
7737-165-5 | CARTA-Workshop Program ACEPHEM | 1078799.17 | 0 |  | 1319.9507
7761-165-5 | CARTA Institutionalization Programme | 0 | 582276.82 |  |  | 712.4373
9100-165-5 | Capital Fund :ACEPHEM | 0 | 377716371.89 |  |  | 462149.9698
9200-165-5 | General Fund: ACEPHEM | 0 | 339457127.83 |  |  | 415338.3677
9300-165-5 | Revaluation Reserve - ACEPHEM | 0 | 111675069.81 |  |  | 136638.5838
Total: |  | 1432985190.17 | 1432985190.17 |  | 1753310.451 | 1753310.451
Net Income (Loss) for Accounts Listed: |  | 68727010.71 |  |  | 84090.0429
48 accounts printed