## Sources and Uses of Funds
COLLEGE OF MEDICINE (UNIVERSITY OF MALAWI)
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT (151847)
Statement of Sources and Uses of Funds
for the semi-annual period ending 31 March 2023
Cummulative for
Sources of Fund | Financial Year End Dec 2022 | Period ending March 2023
| USD | USD
Opening Cash Balance
Government Funds
World Bank IDA Funds | 139457.0388 | 312913.22
Student Fees
Others | 79348.1835 | 99781.3961
Total | 218805.2223 | 412694.6161
Add Receipts
Government Funds
World Bank IDA Funds | 362332.8844 | 360571.9354
Student Fees
Others | 99781.3961 | 250859.1422
Total Financing | 680919.5028 | 1024125.6936
Less: ACE Expenditure as per Project Implementation Plan
1.1 Existing curricula reviewed and improved | 612 | 97319
1.2 Students recruited and supported | 35040.4627 | 25410
1.3 Rehabilitate and upgrade teaching and learning facilities | 537.2143 | 186100
1.4 Professional development and short courses for special groups | 5326.56 | 36809
2.1 Procure general use teaching and research equipment and lab supplies | 1863.3444 | 11618
2.2 Core team to lead public health and herbal medicine research | 37064.8211 | 83532
2.3 Field site monitoring and support and vehicle maintenance | 13866.8112 | 10862
2.4 Facilitating international conference presentations and manuscript publication | 102894.7721 | 18947
3.1 Education outreach program | 42338.9053 | 14512
3.2 Facilitating national and regional student and faculty exchange program | 1260.2721 | 15469
3.3 Proposal development for possible funding (External revenue generation) | 1863.3444 | 22000
3.4 Conduct short courses (as part of external revenue generation) | 17290.1416 | 5560
4.1 International Academic Partners monitoring and support | 3681.3792 | 15420
4.2 MOU signing and joint Implementation Planning meeting | 1367.5523 | 8610
4.3 Partner implementation plan bi-Annual review meeting | 293.026 | 2571
5.1 Project meetings conducted | 2383.278 | 45317
5.3 Administration offices funished and equiped | 541 | 6690
Total Uses of Funds by Components | 268224.8846 | 606746
Closing Balances | 412694.6182 | 417379.6936
Government Funds
World Bank IDA Funds | 312913.22 | 161242.2939
Student Fees
Others (Extenally generated) | 99781.3961 | 256137.4
Total Closing Cash Balance | 412694.6161 | 417379.6939

## Uses of Funds as per PIM
College of Medicine
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT
Uses of Funds (Breakdown)
for the semi-annual period ending…31 Mar 2023
Expenditure | Cummulative for |  |  |  | Period ending Mar 2023 |  | Explanation of | PAD /Life of | Revised
|  | Financial Year Ending Dec 2022 |  |  |  |  | Variance | Project | PAD
| Actual US$ | Planned US$ | Variance US$ | Actual US$ | Planned US$ | Variance US$
Expenditure Classification 1 as per Project Implementation Plan
1.1 Existing curricula reviewed and improved | 612 | 223000 | 222388 | 97319 | 223000 | 125681 | Work is in progress as stakeholders need more time
1.2 Students recruited and supported | 35040.4627 | 578617 | 543576.5373 | 25410 | 578617 | 553207 | proving to be tough to recruit students hence slow Progress
1.3 Rehabilitate and upgrade teaching and learning facilities | 537.2143 | 300000 | 299462.7857 | 186100 | 300000 | 113900 | Done
1.4 Professional development and short courses for special groups | 5326.56 | 95000 | 89673.44 | 36809 | 95000 | 58191 | Work is in progress as stakeholders need more time
2.1 Procure general use teaching and research equipment and lab supplies | 1863.3444 | 85600 | 83736.6556 | 11618 | 85600 | 73982 | Partly procured Equipment more in progress
2.2 Core team to lead public health and herbal medicine research | 37064.8211 | 101300 | 64235.1789 | 83532 | 101300 | 17768 | Work is in progress as stakeholders need more time
2.3 Field site monitoring and support and vehicle maintenance | 13866.8112 | 34600 | 20733.1888 | 10862 | 34600 | 23738 | Cars relatively new hence maintenance costs low
2.4 Facilitating international conference presentations and manuscript publication | 102894.7721 | 106900 | 4005.2279 | 18947 | 106900 | 87953 | Work is in progress as stakeholders need more time
3.1 Education outreach program | 42338.9053 | 47850 | 5511.0947 | 14512 | 47850 | 33338 | In Progress
3.2 Facilitating national and regional student and faculty exchange program | 1260.2721 | 42000 | 40739.7279 | 15469 | 42000 | 26531 | In Progress
3.3 Proposal development for possible funding (External revenue generation) | 1863.3444 | 22000 | 20136.6556 | 22000 | 22000 | 0 | In Progress
3.4 Conduct short courses (as part of external revenue generation) | 17290.1416 | 20000 | 2709.8584 | 5560 | 20000 | 14440 | Work is in progress as stakeholders need more time
4.1 International Academic Partners monitoring and support | 3681.3792 | 34000 | 30318.6208 | 15420 | 34000 | 18580 | Work is in progress as stakeholders need more time
4.2 MOU signing and joint Implementation Planning meeting | 1367.5523 | 11500 | 10132.4477 | 8610 | 11500 | 2890 | Work is in progress as stakeholders need more time
4.3 Partner implementation plan bi-Annual review meeting | 293.026 | 8000 | 7706.974 | 2571 | 8000 | 5429 | In Progress
5.1 Project meetings conducted | 2383.278 | 57600 | 55216.722 | 45317 | 57600 | 12283 | Work is in progress as stakeholders need more time
5.3 Administration offices funished and equiped | 541 | 8400 | 7859 | 6690 | 8400 | 1710 | In Progress
0
| 268224.8846 | 1776367 | 1508142.1154 | 606746 | 1776367 | 1169621

## EEP Statement
COLLEGE OF MEDICINE (UNIVERSITY OF MALAWI)
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT (151847))
Statement of Reimbursable Eligible Expenditure Programs (EEPs)
for the period ending 31 Mar 2023
1028.8
Cummulative for
Eligible Expenditure Program (EEP) | Semi-Annual Period ending June 2022 MK | Semi-Annual Period ending June 2022 US$ | Financial Year End Mar 31, 2023 MK | Financial Year End Mar 31, 2023 US$
EEP 1: Salaries | 9167858838.29 | 11217214.8214 | 12178655820.91 | 11837729.2194
EEP 2: Teaching and laboratory materials | 63716219.21 | 77959.1539 | 115807555.02 | 112565.6639
EEP 3: Printing and stationery | 221595410.21 | 271130.1912 | 211835620.93 | 205905.5413
EEP 4: Communation expenses | 548684968.93 | 671336.3801 | 142593238.27 | 138601.5146
EEP 5: Student Welfare | 4844730.34 | 5927.707 | 43615792.08 | 42394.8212
EEP 6: Fuels and oils | 129575093.08 | 158539.9252 | 277747430.47 | 269972.2302
EEP 7: Utilities | 597228755.59 | 730731.5009 | 801918641.53 | 779469.9082
EEP 8: Insurance | 116371259.14 | 142384.5454 | 89664050.85 | 87154.0152
EEP 9: Maintenance expenses | 477516341.6 | 584258.9288 | 754156982.91 | 733045.2789
EEP 10: Training and staff development | 153340686.88 | 187618.0094 | 241324768.91 | 234569.1766
Total EEPs | 11480732303.27 | 14047101.1634 | 14857319901.88 | 14441407.3696

## DLI Statement
COLLEGE OF MEDICINE (UNIVERSITY OF MALAWI)
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT (151847)
NOTES ANNEX
DISBURSEMENT LINKED TO INDICATORS | ACTIONS TO BE COMPLETED | STATUS OF ACTIONS COMPLETION | AMOUNT ALLOCATED | AMOUNT DISBURSED | UNDISBURSED BALANCE
DLR 1.1 Signing of the performance and funding agreements and establishing national steering committee | Completion of effectiveness conditions | Done | 600000 | 600000 | 0
DLR 1.2 Development of the project implementation plan | Detailed implemetation plans for ACE approved by ministry in charge of higher education | Done | 500000 | 500000 | 0
DLR 2.1 Timely implementation of annual work plans | Timely execution of annual work plan | 60% completed | 0 | 0 | 0
DLR 2.2 Newly enrolled students in the ACE of which at least 20% must be regional African students | Enrol 126MSc and 10PhD students | Enrolled 140 MSc and 18 PhD students | 1300000 | 711050.03 | 588949.97
DLR 2.3 Quality accrediatation for education programs | Accreditation at National level submitted to NCHE | All 5 programs not yet accredited | 600000 | 300000 | 300000
DLR 2.4 partnership for collaboration in applied research and training | To sign 6 MoUs | Done | 200000 | 200000 | 0
DLR 2.5 peer reviewed journal papers or peer reviewed conference papers prepared collaboratively with national, regional or international co authors | Publish 5 papers | Done | 500000 | 500000 | 0
DLR 2.6 faculty and PHD student exchanges to promote regional research and teraching collaborations | 8 national, 24 regional and 8 international faculty exchanged | 7 faculty, 1 PhD and 2 Technical staff sent, whilst 3 came to COM (1 national and 2 international), awaiting 10 staff from RUFORUM universities | 700000 | 171000 | 529000
DLR 2.7 External revenue generation | Generate $900,000 | Done | 900000 | 900000 | 0
DLR 2.8 institution participating in benchmarking exercise | To enroll for benchmarking under PASET this year 2018 | Done | 100000 | 100000 | 0
DLR 3.1 Timely withdrawal applications supported by interim unaudited financial reports | Internal audit committee produces unaudited financial report | In place | 75000 | 60000 | 15000
DLR 3.2 Functioning audit committee | Formation of Internal audit committee and minutes available | In place | 75000 | 60000 | 15000
DLR 3.3 Functioning internal audit unit | Formation of Internal audit committee and minutes available | In place | 75000 | 45000 | 30000
DLR 3.4 Transparency of financial management | Setting up financial management dissemination channels | In place | 75000 | 30000 | 45000
DLR 4.1 timely procurement audit reports | Produce procurement report together with finacial report | Procurement report available with financial report | 150000 | 120000 | 30000
DLR 4.2timely and satisfactory procurement progress report | Postings done on WB site | Completed and in progress for subsequent reports. | 150000 | 120000 | 30000
|  |  | 6000000 | 4417050.03 | 1582949.97
0.73618

## AWP
ANNEX: DETAILED ACTIVITIES
ACTIVITY NAME | Quantity |  | Budget USD | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE
1.1 Existing curricula reviewed and improved | bar: JUL to JUNE
1.1.1 To hold a regional consultative stakeholder meeting for curriculum development or review (regional, international, and local partners)
1.1.2 Cost for accomodation | 25 | 180 | 4500
1.1.3 Visit by ACEPHEM leaders to 2 partner institutions | 4 | 3000 | 12000
1.1.4 Meals | 25 | 100 | 2500
1.1.5 Local transportation | 1 | 1500 | 1500
1.1.6 Resource person | 1 | 1500 | 1500
1.1.7 Workshop management | 1 | 1000 | 1000
1.1.8 Accreditation fees | 1 | 200000 | 200000
SUB-TOTAL |  |  | 223000
1.2 Students recruited and supported | bar: JUL to JUNE
1.2.1 Tuition support for PhD Students | 11 | 10000 | 110000
1.2.1.1 Tuition support for Masters Students | 34 | 3200 | 108800
1.2.2 Stipend support for Post Graduate students | 19 | 7200 | 136800
1.2.3. Internship Support | 5 | 750 | 3750
1.2.4 Internship research funds support | 5 | 533.4 | 2667
1.2.4 Masters research funds support | 15 | 10000 | 150000
1.2.4 Phd research funds support | 4 | 10000 | 40000
1.2.5 Recruitment of students costs | 1 | 6000 | 6000
1.2.8 Scholarship incentive: Regional PhD students each expected to publish 3 articles before graduating | 3 | 300 | 900
1.2.8 Scholarship incentive: National PhD students each expected to publish 3 articles before graduating | 16 | 300 | 4800
1.2.9 Regional Masters students each expected to publish at least one paper before graduating | 6 | 100 | 600
1.2.10 National Masters students each expected to publish at least one paper before graduating | 71 | 102.8169 | 7300
1.2.11 Communications with institutions and partners | 1 | 7000 | 7000
SUB TOTAL |  |  | 578617
1.3 Rehabilitate and upgrade teaching and learning facilities
1.3.1 Purchasing of ODL premises | 1 | 300000 | 300000 | bar: OCT to FEB
300000
1.4 Professional development and short courses for special groups | bar: JUL to JUNE
1.4.1 Training Needs assesment | 1 | 3000 | 3000
1.4.2 Refreshments | 10 | 1000 | 10000
1.4.3 Workshop management (Stationery) | 10 | 200 | 2000
1.4.4 Facilitators allowances | 10 | 3000 | 30000
1.4.5 Per Diems for participants (Partners) | 10 | 1000 | 10000
1.4.6 Accomodation | 10 | 2500 | 25000
1.4.7 Travel for non-national delegates | 4 | 1500 | 6000
1.4.8 Travel for national delegates | 6 | 1500 | 9000
SUB-TOTAL |  |  | 95000
2.1 Procure general use teaching and research equipment and lab supplies
2.1.1 Purchase of ICT equipment (Laptops, projectors and Accesories) | 15 | 1000 | 15000 | bar: SEP
2.1.2 Maintenance of heavy duty photocopier | 1 | 8000 | 8000 | bar: JUL
2.1.3 General Lab Equipment and supplies | 1 | 50000 | 50000 | bar: JUL to JUNE
2.1.4 Students travels and lodging to partner institutions | 5 | 2520 | 12600 | bar: SEP to DEC
SUB-TOTAL |  |  | 85600
2.2 Core team to lead public health and herbal medicine research | bar: JUL to JUNE
2.2.1 Salaries for ACEPHEM staff | 4 | 11200 | 44800
2.2.2 Development of Herbal Medicine research agenda | 1 | 26500 | 26500
1.2.3 Masters and PhD for Faculty | 1 | 30000 | 30000
SUB-TOTAL |  |  | 101300
2.3 Field site monitoring and support and vehicle maintenance | bar: JUL to JUNE
2.3.1 Vehicle maintenance and fuel | 2 | 5300 | 10600
2.3.2 Monitoring and supportive visits to partner institutions | 4 | 6000 | 24000
SUB-TOTAL |  |  | 34600
2.4 Facilitating international conference presentations and manuscript publication | bar: JUL to JUNE
2.4.1 Per Diems for participants (Partners) | 3 | 1000 | 3000
2.4.2 Travel costs | 3 | 1300 | 3900
2.4.3 Publication fees | 10 | 300 | 3000
2.4.4 Paying for international conferences | 10 | 200 | 2000
2.4.5 Research costs for staff | 5 | 1000 | 5000
SUB-TOTAL |  |  | 16900
3.1 Education outreach program | bar: JUL to JUNE
3.1.1 Maintenance of ACEPHEM website | 1 | 2000 | 2000
3.1.2 High School Science Teachers training | 5 | 530 | 2650
3.1.3 Open day | 1 | 1200 | 1200
3.1.4 Community Outreach | 1 | 2000 | 2000
SUB-TOTAL |  |  | 7850
3.2 Facilitating national and regional student and faculty exchange program | bar: JUL to JUNE
3.2.1 Accomodation | 8 | 2500 | 20000
3.2.2 Travel costs | 8 | 1500 | 12000
SUB-TOTAL |  |  | 32000
3.3 Proposal development for possible funding (External revenue generation)
3.3.1 Allowances | 20 | 500 | 10000
3.3.2 Conference Package | 3 | 2500 | 7500
3.3.3 Travel Cost for Local Partners | 3 | 1500 | 4500
SUB TOTAL |  |  | 22000
3.4 Conduct short courses (as part of external revenue generation) | 2 | 10000 | 20000 | bar: JUL to JUNE
4.1 International Academic Partners monitoring and support | bar: JUL to JUNE
4.1.1 Travel | 4 | 1500 | 6000
4.1.2 Accomodation | 4 | 2000 | 8000
4.1.4 Meetings with partners | 4 | 2500 | 10000
4.1.5 Grant writing meetings with partner institutions | 4 | 2500 | 10000
SUB-TOTAL |  |  | 34000
4.2 MOU signing and joint Implementation Planning meeting
4.2.1 Conference Package | 2 | 4000 | 8000
4.2.2 Per diem for local partners | 3 | 500 | 1500
4.2.3 Refreshments | 10 | 200 | 2000
4.2.5 Travel cost and perdiems (International) | 10 | 4000 | 40000
SUB TOTAL |  |  | 51500
4.3 Partner implementation plan bi-Annual review meeting | bar: JUL to JUNE
4.3.1 Conference Package | 1 | 4000 | 4000
4.3.2 Per diem for local partners | 3 | 500 | 1500
4.3.3 Refreshments | 1 | 1000 | 1000
4.3.5 Travel cost for local Partners | 10 | 150 | 1500
SUB TOTAL |  |  | 8000
5.1 Project meetings conducted | bar: JUL to JUNE
5.2.1 Accomodation for ISAB meeting | 2 | 13333 | 26666
5.2.1 Per diems for ISAB meeting | 2 | 3200 | 6400
5.2.3 Visa cost | 2 | 1400 | 2800
5.2.4 Local travel | 2 | 1500 | 3000
5.2.5 Conference package | 2 | 4000 | 8000
5.2.6 Travel Cost (International) | 2 | 15000 | 30000
5.2.7 Accomodation for National Steering meeting | 10 | 400 | 4000
5.2.8 Travel for National Steering meeting | 10 | 300 | 3000
5.2.9 Conference Package | 1 | 1000 | 1000
5.3.1 Per diem for local steering committee meeting | 5 | 400 | 2000
5.3.2 Refreshments for local steering committee meeting | 1 | 400 | 400
5.3.3 Per diem for local steering committee meeting |  |  | 26734
5.3.4 Travel cost for local steering committee meeting | 8 | 600 | 4800
0
5.2.8 Per diem for sub-committee meeting | 5 | 400 | 2000
5.2.7 Per diem for sub-committee meeting |  |  | 0
5.2.9 Refreshments for sub-committee meeting | 1 | 400 | 400
5.3.0 Travel cost for sub-committee meeting | 4 | 600 | 2400
5.3.1 ACEPHEM members travel cost | 4 | 1500 | 6000
5.3.2 Capacity Building Workshops for ACEPHEM Staff | 4 | 7000 | 28000
SUB-TOTAL |  |  | 157600
5.3 Administration offices funished and equiped | bar: JUL to JUNE
5.3.1 Office furniture | 1 | 3000 | 3000
5.3.2 Communication | 12 | 250 | 3000
5.3.3 General Office supplies | 12 | 200 | 2400
8400
GRAND TOTAL |  |  | 1776367
0

## Mar 2023 TB & Financials
Account Number | Description | Debits | Credits | 1028.8 | Debits | Credits
|  | MKW | MKW |  | USD | USD
1000-165-5 | Grants received : ACE PHEM | 0 | 370956407.09 |  |  | 360571.9354
1400-165-5 | Interest received : ACE PHEM | 0 | 918940.9 |  |  | 893.2163
1900-165-5 | Other Income : ACE PHEM | 0 | 196866447.82 |  |  | 191355.412
1920-165-5 | Exchange Gain: ACEPHEM | 0 | 60298496.81 | 629040292.62 |  | 58610.514 | 611431.0776
2000-165-5 | Staff costs : - ACEPHEM | 81884105.47 | 0 |  | 79591.8599
2500-165-5 | Stationery and Printing costs : ACE PHEM | 2965298.9 | 0 |  | 2882.289
2605-165-5 | Lab Supplies : ACE PHEM | 4382213.75 | 0 |  | 4259.539
2801-165-5 | Advertisements : ACE PHEM | 229823.34 | 0 |  | 223.3897
2900-165-5 | General research expenses : - ACEPHEM | 71221545.46 | 0 |  | 69227.7852
3652-165-5 | Meeting Expenses : -ACEPHEM | 38211078.71 | 0 |  | 37141.4062
3701-165-5 | Fuel : - ACEPHEM | 15918203.16 | 0 |  | 15472.5925
3702-165-5 | Subsistene allowance : ACE PHEM | 65373801.49 | 0 |  | 63543.7417
3706-165-5 | Vehicle Hiring : ACEPHEM | 220042 | 0 |  | 213.8822
3708-165-5 | Workshops / Meetings : ACE PHEM | 77962622.74 | 0 |  | 75780.1543
3800-165-5 | External travel : ACE PHEM | 1290266.59 | 0 |  | 1254.1472
3801-165-5 | Cost of Airticket : ACE PHEM | 11454380 | 0 |  | 11133.7286
3851-165-5 | Communication : ACE PHEM | 4626000 | 0 |  | 4496.5008
3900-165-5 | Maintainance of Motor vehicle : ACE PHEM | 11870551.07 | 0 |  | 11538.2495
4100-165-5 | Maintainance of equipment : COM Acephem Project | 550000 | 0 |  | 534.6034
4301-165-5 | Fellowship Programmes : ACE PHEM | 88513256.46 | 0 |  | 86035.4359
4303-165-5 | Training Professional subscription : ACE PHEM | 300000 | 0 |  | 291.6019
4600-165-5 | General expenses : - ACEPHEM | 19048243.6 | 0 |  | 18515.0113
4610-165-5 | Bank Charges : ACE PHEM | 1720983.55 | 0 |  | 1672.8067
4910-165-5 | Special Expense-Buildings : ACEPHEM | 140000000 | 0 |  | 136080.8709 | 0
4920-165-5 | Special Expense-Office Equipment : ACE PHEM | 1398000 | 0 |  | 1358.8647
4925-165-5 | Special Expense-Computers : - ACE PHEM | 13921400 | 0 | 653061816.29 | 13531.6874 |  | 634780.148
5000-165-5 | Property -Land : COM Acephem Project | 140000000 | 0 |  | 136080.8709
5009-165-5 | Work in Progress - Buildings : ACEPHEM | 0 | 0 |  | 0
5010-165-5 | Lands & Buildings : ACEPHEM | 473955333 | 0 |  | 460687.5321
5200-165-5 | Office equipment : -ACEPHEM | 35001241.38 | 0 |  | 34021.4244
5210-165-5 | Computers - ACEPHEM | 24428150.12 | 0 |  | 23744.3139
5220-165-5 | Laboratory & Hospital Equipment: ACEPHEM | 11829000 | 0 |  | 11497.8616 | 0
5300-165-5 | Furniture and fittings : ACEPHEM | 5767375 | 0 |  | 5605.9244 | 0
5400-165-5 | Motor vehicles : ACEPHEM | 137397726.31 | 0 |  | 133551.4447 | 0
5500-165-5 | Accumm Depn - Land & Buildings : ACEPHEM | 0 | 51040971.42 |  |  | 49612.1417
5502-165-5 | Accumm Depn - Furniture & Fittings :ACEPHEM | 0 | 5707793.75 |  |  | 5548.011
5503-165-5 | Accumm Depn - Motor Vehicles :ACEPHEM | 0 | 113216519.56 |  |  | 110047.1613
5506-165-5 | Accumm Depn - Office Equipment : ACEPHEM | 0 | 27391010.18 |  | 0 | 26624.2323
5507-165-5 | Accumm Depn - Computers : ACEPHEM | 0 | 18332055.08 |  | 0 | 17818.8716
5509-165-5 | Accumm Depn - Laboratory & Hospital Equipment - ACEPHEM | 0 | 12420450 |  | 0 | 12072.7547
6000-165-5 | Debtors Transactions : ACE PHEM | 81297719.32 | 0 |  | 79021.8889
6438-165-5 | African Centre for Public Health and Herbal Medicine FCDA | 119938972.67 | 0 |  | 116581.4276 | 0
6439-165-5 | African Centre for Public Health and Herbal Medicine Local | 45947099.34 | 0 |  | 44660.8664 | 0
6800-165-5 | Cash Imprest - ACE PHEM Cash Imprest | 5894187.25 | 0 |  | 5729.1867
7201-165-5 | Withholding Tax Control Account : ACE PHEM | 190226.39 | 0 |  | 184.9012 | 0
7204-165-5 | VAT Control Account : ACE PHEM | 0 | 1580992.89 |  |  | 1536.7349
7730-165-5 | ICARTA PROJECT | 0 | 0 |  |  | 0
7737-165-5 | CARTA-Workshop Program ACEPHEM | 1078799.17 | 0 |  | 1048.5995 | 0
7761-165-5 | CARTA Institutionalization Programme | 0 | 582276.82 |  |  | 565.9767
9100-165-5 | Capital Fund :ACEPHEM | 0 | 483764667.01 |  |  | 470222.2658
9200-165-5 | General Fund: ACEPHEM | 0 | 276205258.1 |  |  | 268473.2291
9300-165-5 | Revaluation Reserve - ACEPHEM | 0 | 116505358.81 |  |  | 113243.9335
Total: |  | 1735787646.24 | 1735787646.24 |  | 1687196.3902 | 1687196.3902
Net Income (Loss) for Accounts Listed: |  | 24021523.67 |  |  | 23349.0704