## Sources and Uses of Funds
COLLEGE OF MEDICINE (UNIVERSITY OF MALAWI)
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT (151847)
Statement of Sources and Uses of Funds
for the semi-annual period ending 30 SEPT 2024
Cummulative for
Sources of Fund | Financial Year End Mar 2024 | Period ending Sept 2024
| USD | USD
Opening Cash Balance
Government Funds
World Bank IDA Funds | 112474.35 | 214912.9
Student Fees
Others | 280382.83 | 247630.5788
Total | 392857.18 | 462543.4788
Add Receipts
Government Funds
World Bank IDA Funds | 0 | 403845.75
Student Fees
Others | 322608.3897 | 100244.01
Total Financing | 715465.5697 | 966633.2388
Less: ACE Expenditure as per Project Implementation Plan
1.1 Existing curricula reviewed and improved | 27567 | 39750
1.2 Students recruited and supported | 24100 | 8362.8972
1.3 Rehabilitate and upgrade teaching and learning facilities | 9941.2581 | 13337.5428
1.4 Professional development and short courses for special groups | 2541 | 3968.3837
2.1 Procure general use teaching and research equipment and lab supplies | 9120 | 11810.2473
2.2 Core team to lead public health and herbal medicine research | 12575.58 | 25641
2.3 Field site monitoring and support and vehicle maintenance | 1897 | 7264.7711
2.4 Facilitating international conference presentations and manuscript publication | 33730.4468 | 26022.4534
3.1 Education outreach program | 9754 | 7880
3.2 Facilitating national and regional student and faculty exchange program | 2875 | 1181.7399
3.3 Proposal development for possible funding (External revenue generation) | 33893.0558 | 30086.8215
3.4 Conduct short courses (as part of external revenue generation) | 7841 | 11429.5302
4.1 International Academic Partners monitoring and support | 40140.7506 | 15434.3615
4.2 MOU signing and joint Implementation Planning meeting | 5794 | 6934.3109
4.3 Partner implementation plan bi-Annual review meeting | 5740 | 14007.9977
5.1 Project meetings conducted | 25412 | 7797.4529
5.3 Administration offices funished and equiped | 0
Total Uses of Funds by Components | 252922.0913 | 230909.5101
Closing Balances | 462543.4784 | 735723.7287
Government Funds
World Bank IDA Funds | 214912.9 | 451521.1
Student Fees
Others (Extenally generated) | 247630.5788 | 284202.63
Total Closing Cash Balance | 462543.4788 | 735723.73

## Uses of Funds as per PIM
College of Medicine
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT
Uses of Funds (Breakdown)
for the semi-annual period ending…30 Sept 2024
Expenditure | Cummulative for |  |  |  | Period ending September 2024 |  | Explanation of | PAD /Life of | Revised
|  | Financial Year Ending March 2024 |  |  |  |  | Variance | Project | PAD
| Actual US$ | Planned US$ | Variance US$ | Actual US$ | Planned US$ | Variance US$
Expenditure Classification 1 as per Project Implementation Plan
1.1 Existing curricula reviewed and improved | 27567 | 125681 | 89945.6863 | 39750 | 98114 | 58364 | Work is in progress as stakeholders need more time
1.2 Students recruited and supported | 24100 | 553207 | 530171.2201 | 54937.8772 | 529107 | 474169.1228 | proving to be tough to recruit students hence slow Progress
1.3 Rehabilitate and upgrade teaching and learning facilities | 9941.2581 | 113900 | 113709.4771 | 13337.5428 | 103958.7419 | 90621.1991 | Done
1.4 Professional development and short courses for special groups | 2541 | 58191 | 56658.2553 | 3968.3837 | 55650 | 51681.6163 | Work is in progress as stakeholders need more time
2.1 Procure general use teaching and research equipment and lab supplies | 9120 | 73982 | 71583.2993 | 11810.2473 | 64862 | 53051.7527 | Partly procured Equipment more in progress
2.2 Core team to lead public health and herbal medicine research | 12575.58 | 17768 | 7091.4232 | 3690 | 5192.42 | 1502.42 | Work is in progress as stakeholders need more time
2.3 Field site monitoring and support and vehicle maintenance | 1897 | 23738 | 21906.0675 | 7264.7711 | 21841 | 14576.2289 | Cars relatively new hence maintenance costs low
2.4 Facilitating international conference presentations and manuscript publication | 33730.4468 | 87953 | 69152.1539 | 26022.4534 | 54222.5532 | 28200.0998 | Work is in progress as stakeholders need more time
3.1 Education outreach program | 9754 | 33338 | 32877.2691 | 7880 | 23584 | 15704 | In Progress
3.2 Facilitating national and regional student and faculty exchange program | 2875 | 26531 | 23504.1726 | 1181.7399 | 23656 | 22474.2601 | In Progress
3.3 Proposal development for possible funding (External revenue generation) | 33893.0558 | 69754 | 0 | 30086.8215 | 35860.9442 | 5774.1227 | In Progress
3.4 Conduct short courses (as part of external revenue generation) | 7841 | 14440 | 13249.4936 | 4510 | 6599 | 2089 | Work is in progress as stakeholders need more time
4.1 International Academic Partners monitoring and support | 40140.7506 | 58580 | 14932.0537 | 15434.3615 | 18439.2494 | 3004.8879 | Work is in progress as stakeholders need more time
4.2 MOU signing and joint Implementation Planning meeting | 5794 | 12890 | 790 | 6934.3109 | 7096 | 161.6891 | Work is in progress as stakeholders need more time
4.3 Partner implementation plan bi-Annual review meeting | 5740 | 7429 | 4945.129 |  | 1689 | 1689 | In Progress
5.1 Project meetings conducted | 25412 | 32283 | 10667.68 | 4101 | 6871 | 2770 | Work is in progress as stakeholders need more time
5.3 Administration offices funished and equiped |  | 1710 | 1710 | 0 | 1710 | 1710 | In Progress
| 252922.0913 | 1311375 | 1062893.3807 | 230909.5094 | 1058452.9087 | 827543.3993
1776367

## EEP Statement
COLLEGE OF MEDICINE (UNIVERSITY OF MALAWI)
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT (151847))
Statement of Reimbursable Eligible Expenditure Programs (EEPs)
for the period ending 30 Sept 2024
1733.8333
Cummulative for
Eligible Expenditure Program (EEP) | Financial Year End Mar 31, 2024 MK | Financial Year End Mar 31, 2024 US$ | Financial Year End Sept 30, 2024 MK | Financial Year End Sept 30, 2024 US$
EEP 1: Salaries | 21135389682.62 | 12189977.9423 | 14847612880.3774 | 8563460.4436
EEP 2: Teaching and laboratory materials | 192743324.84 | 111166.007 | 94316954.02 | 54397.9367
EEP 3: Printing and stationery | 292159524.69 | 168504.968 | 185938363.61 | 107241.2
EEP 4: Communation expenses | 366422331.56 | 211336.5406 | 145852174.24 | 84121.221
EEP 5: Student Welfare | 5797097 | 3343.5146 | 63333 | 36.5277
EEP 6: Fuels and oils | 432205743.14 | 249277.565 | 386976329.87 | 223191.1971
EEP 7: Utilities | 623944322.38 | 359864.0783 | 944930763.27 | 544995.1638
EEP 8: Insurance | 333505174.05 | 192351.3489 | 244406532.05 | 140963.1088
EEP 9: Maintenance expenses | 4198047383.48 | 2421252.022 | 2782304029.91 | 1604712.5349
EEP 10: Training and staff development | 217371316.22 | 125370.3665 | 186699310.47 | 107680.0812
Total EEPs | 27797585899.98 | 16032444.3532 | 19819100670.8174 | 11430799.4147

## DLI Statement
COLLEGE OF MEDICINE (UNIVERSITY OF MALAWI)
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT (151847)
NOTES ANNEX
DISBURSEMENT LINKED TO INDICATORS | ACTIONS TO BE COMPLETED | STATUS OF ACTIONS COMPLETION | AMOUNT ALLOCATED | AMOUNT DISBURSED | UNDISBURSED BALANCE
DLR 1.1 Signing of the performance and funding agreements and establishing national steering committee | Completion of effectiveness conditions | Done | 600000 | 600000 | 0
DLR 1.2 Development of the project implementation plan | Detailed implemetation plans for ACE approved by ministry in charge of higher education | Done | 500000 | 500000 | 0
DLR 2.1 Timely implementation of annual work plans | Timely execution of annual work plan | 60% completed | 0 | 0 | 0
DLR 2.2 Newly enrolled students in the ACE of which at least 20% must be regional African students | Enrol 126MSc and 10PhD students | Enrolled 140 MSc and 18 PhD students | 1300000 | 1224655.25 | 75344.75
DLR 2.3 Quality accrediatation for education programs | Accreditation at National level submitted to NCHE | All 5 programs not yet accredited | 600000 | 300000 | 300000
DLR 2.4 partnership for collaboration in applied research and training | To sign 6 MoUs | Done | 200000 | 200000 | 0
DLR 2.5 peer reviewed journal papers or peer reviewed conference papers prepared collaboratively with national, regional or international co authors | Publish 5 papers | Done | 500000 | 500000 | 0
DLR 2.6 faculty and PHD student exchanges to promote regional research and teraching collaborations | 8 national, 24 regional and 8 international faculty exchanged | 7 faculty, 1 PhD and 2 Technical staff sent, whilst 3 came to COM (1 national and 2 international), awaiting 10 staff from RUFORUM universities | 700000 | 700000 | 0
DLR 2.7 External revenue generation | Generate $900,000 | Done | 900000 | 900000 | 0
DLR 2.8 institution participating in benchmarking exercise | To enroll for benchmarking under PASET this year 2018 | Done | 100000 | 100000 | 0
DLR 3.1 Timely withdrawal applications supported by interim unaudited financial reports | Internal audit committee produces unaudited financial report | Done | 75000 | 75000 | 0
DLR 3.2 Functioning audit committee | Formation of Internal audit committee and minutes available | Done | 75000 | 75000 | 0
DLR 3.3 Functioning internal audit unit | Formation of Internal audit committee and minutes available | Done | 75000 | 75000 | 0
DLR 3.4 Transparency of financial management | Setting up financial management dissemination channels | Done | 75000 | 75000 | 0
DLR 4.1 timely procurement audit reports | Produce procurement report together with finacial report | Procurement report available with financial report | 150000 | 150000 | 0
DLR 4.2timely and satisfactory procurement progress report | Postings done on WB site | Completed and in progress for subsequent reports. | 150000 | 150000 | 0
|  |  | 6000000 | 5624655.25 | 375344.75
0.93744
5624655.25
0

## AWP
ANNEX: DETAILED ACTIVITIES
ACTIVITY NAME | Quantity |  | Budget USD | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE
1.1 Existing curricula reviewed and improved | bar: JUL to JUNE
1.1.1 To hold a regional consultative stakeholder meeting for curriculum development or review (regional, international, and local partners)
1.1.2 Cost for accomodation | 25 | 180 | 4500
1.1.3 Visit by ACEPHEM leaders to 2 partner institutions | 4 | 3000 | 12000
1.1.4 Meals | 25 | 100 | 2500
1.1.5 Local transportation | 1 | 1500 | 1500
1.1.6 Resource person | 1 | 1500 | 1500
1.1.7 Workshop management | 1 | 1000 | 1000
1.1.8 Accreditation fees | 1 | 200000 | 200000
SUB-TOTAL |  |  | 223000
1.2 Students recruited and supported | bar: JUL to JUNE
1.2.1 Tuition support for PhD Students | 11 | 10000 | 110000
1.2.1.1 Tuition support for Masters Students | 34 | 3200 | 108800
1.2.2 Stipend support for Post Graduate students | 19 | 7200 | 136800
1.2.3. Internship Support | 5 | 750 | 3750
1.2.4 Internship research funds support | 5 | 533.4 | 2667
1.2.4 Masters research funds support | 15 | 10000 | 150000
1.2.4 Phd research funds support | 4 | 10000 | 40000
1.2.5 Recruitment of students costs | 1 | 6000 | 6000
1.2.8 Scholarship incentive: Regional PhD students each expected to publish 3 articles before graduating | 3 | 300 | 900
1.2.8 Scholarship incentive: National PhD students each expected to publish 3 articles before graduating | 16 | 300 | 4800
1.2.9 Regional Masters students each expected to publish at least one paper before graduating | 6 | 100 | 600
1.2.10 National Masters students each expected to publish at least one paper before graduating | 71 | 102.8169 | 7300
1.2.11 Communications with institutions and partners | 1 | 7000 | 7000
SUB TOTAL |  |  | 578617
1.3 Rehabilitate and upgrade teaching and learning facilities
1.3.1 Purchasing of ODL premises | 1 | 300000 | 300000 | bar: OCT to FEB
300000
1.4 Professional development and short courses for special groups | bar: JUL to JUNE
1.4.1 Training Needs assesment | 1 | 3000 | 3000
1.4.2 Refreshments | 10 | 1000 | 10000
1.4.3 Workshop management (Stationery) | 10 | 200 | 2000
1.4.4 Facilitators allowances | 10 | 3000 | 30000
1.4.5 Per Diems for participants (Partners) | 10 | 1000 | 10000
1.4.6 Accomodation | 10 | 2500 | 25000
1.4.7 Travel for non-national delegates | 4 | 1500 | 6000
1.4.8 Travel for national delegates | 6 | 1500 | 9000
SUB-TOTAL |  |  | 95000
2.1 Procure general use teaching and research equipment and lab supplies
2.1.1 Purchase of ICT equipment (Laptops, projectors and Accesories) | 15 | 1000 | 15000 | bar: SEP
2.1.2 Maintenance of heavy duty photocopier | 1 | 8000 | 8000 | bar: JUL
2.1.3 General Lab Equipment and supplies | 1 | 50000 | 50000 | bar: JUL to JUNE
2.1.4 Students travels and lodging to partner institutions | 5 | 2520 | 12600 | bar: SEP to DEC
SUB-TOTAL |  |  | 85600
2.2 Core team to lead public health and herbal medicine research | bar: JUL to JUNE
2.2.1 Salaries for ACEPHEM staff | 4 | 11200 | 44800
2.2.2 Development of Herbal Medicine research agenda | 1 | 26500 | 26500
1.2.3 Masters and PhD for Faculty | 1 | 30000 | 30000
SUB-TOTAL |  |  | 101300
2.3 Field site monitoring and support and vehicle maintenance | bar: JUL to JUNE
2.3.1 Vehicle maintenance and fuel | 2 | 5300 | 10600
2.3.2 Monitoring and supportive visits to partner institutions | 4 | 6000 | 24000
SUB-TOTAL |  |  | 34600
2.4 Facilitating international conference presentations and manuscript publication | bar: JUL to JUNE
2.4.1 Per Diems for participants (Partners) | 3 | 1000 | 3000
2.4.2 Travel costs | 3 | 1300 | 3900
2.4.3 Publication fees | 10 | 300 | 3000
2.4.4 Paying for international conferences | 10 | 200 | 2000
2.4.5 Research costs for staff | 5 | 1000 | 5000
SUB-TOTAL |  |  | 16900
3.1 Education outreach program | bar: JUL to JUNE
3.1.1 Maintenance of ACEPHEM website | 1 | 2000 | 2000
3.1.2 High School Science Teachers training | 5 | 530 | 2650
3.1.3 Open day | 1 | 1200 | 1200
3.1.4 Community Outreach | 1 | 2000 | 2000
SUB-TOTAL |  |  | 7850
3.2 Facilitating national and regional student and faculty exchange program | bar: JUL to JUNE
3.2.1 Accomodation | 8 | 2500 | 20000
3.2.2 Travel costs | 8 | 1500 | 12000
SUB-TOTAL |  |  | 32000
3.3 Proposal development for possible funding (External revenue generation)
3.3.1 Allowances | 20 | 500 | 10000
3.3.2 Conference Package | 3 | 2500 | 7500
3.3.3 Travel Cost for Local Partners | 3 | 1500 | 4500
SUB TOTAL |  |  | 22000
3.4 Conduct short courses (as part of external revenue generation) | 2 | 10000 | 20000 | bar: JUL to JUNE
4.1 International Academic Partners monitoring and support | bar: JUL to JUNE
4.1.1 Travel | 4 | 1500 | 6000
4.1.2 Accomodation | 4 | 2000 | 8000
4.1.4 Meetings with partners | 4 | 2500 | 10000
4.1.5 Grant writing meetings with partner institutions | 4 | 2500 | 10000
SUB-TOTAL |  |  | 34000
4.2 MOU signing and joint Implementation Planning meeting
4.2.1 Conference Package | 2 | 4000 | 8000
4.2.2 Per diem for local partners | 3 | 500 | 1500
4.2.3 Refreshments | 10 | 200 | 2000
4.2.5 Travel cost and perdiems (International) | 10 | 4000 | 40000
SUB TOTAL |  |  | 51500
4.3 Partner implementation plan bi-Annual review meeting | bar: JUL to JUNE
4.3.1 Conference Package | 1 | 4000 | 4000
4.3.2 Per diem for local partners | 3 | 500 | 1500
4.3.3 Refreshments | 1 | 1000 | 1000
4.3.5 Travel cost for local Partners | 10 | 150 | 1500
SUB TOTAL |  |  | 8000
5.1 Project meetings conducted | bar: JUL to JUNE
5.2.1 Accomodation for ISAB meeting | 2 | 13333 | 26666
5.2.1 Per diems for ISAB meeting | 2 | 3200 | 6400
5.2.3 Visa cost | 2 | 1400 | 2800
5.2.4 Local travel | 2 | 1500 | 3000
5.2.5 Conference package | 2 | 4000 | 8000
5.2.6 Travel Cost (International) | 2 | 15000 | 30000
5.2.7 Accomodation for National Steering meeting | 10 | 400 | 4000
5.2.8 Travel for National Steering meeting | 10 | 300 | 3000
5.2.9 Conference Package | 1 | 1000 | 1000
5.3.1 Per diem for local steering committee meeting | 5 | 400 | 2000
5.3.2 Refreshments for local steering committee meeting | 1 | 400 | 400
5.3.3 Per diem for local steering committee meeting |  |  | 26734
5.3.4 Travel cost for local steering committee meeting | 8 | 600 | 4800
0
5.2.8 Per diem for sub-committee meeting | 5 | 400 | 2000
5.2.7 Per diem for sub-committee meeting |  |  | 0
5.2.9 Refreshments for sub-committee meeting | 1 | 400 | 400
5.3.0 Travel cost for sub-committee meeting | 4 | 600 | 2400
5.3.1 ACEPHEM members travel cost | 4 | 1500 | 6000
5.3.2 Capacity Building Workshops for ACEPHEM Staff | 4 | 7000 | 28000
SUB-TOTAL |  |  | 157600
5.3 Administration offices funished and equiped | bar: JUL to JUNE
5.3.1 Office furniture | 1 | 3000 | 3000
5.3.2 Communication | 12 | 250 | 3000
5.3.3 General Office supplies | 12 | 200 | 2400
8400
GRAND TOTAL |  |  | 1776367
0

## Sept 2024 TB & Financials
ACEPHEM
Trial Balance September 2024 |  |  |  |  | 1733.8333
| 2024 |  |  |  | USD | USD
|  |  | DR | CR | DR | CR
1070 - Grants Received | C013 - Projects Blantyre | D614 - ACEPHEM | 0 | 1674411658.49 |  | 965728.1692
1080 - Interest - Deposits | C013 - Projects Blantyre | D614 - ACEPHEM | 0 | 1569240.51 |  | 905.07 | 966633.2392
2000 - Salaries & Wages:(Payroll Based) | C013 - Projects Blantyre | D614 - ACEPHEM | 135974911.1 | 0 | 78424.4432 | 0
2001 - Wages/Casual Labourers and Part time(Outside Payroll) | C013 - Projects Blantyre | D614 - ACEPHEM | 13662606.41 | 0 | 7880
2005 - Allowances | C013 - Projects Blantyre | D614 - ACEPHEM | 26760610 | 0 | 15434.3615
2050 - Superannuation Costs: | C013 - Projects Blantyre | D614 - ACEPHEM | 2504129.64 | 0 | 1444.2736
2101 - General Research and Publication costs | C013 - Projects Blantyre | D614 - ACEPHEM | 19816900 | 0 | 11429.5302
2300 - Training & Staff Development: | C013 - Projects Blantyre | D614 - ACEPHEM | 980386.23 | 0 | 565.4443
2401 - Conferences & Workshops: | C013 - Projects Blantyre | D614 - ACEPHEM | 13519483.5 | 0 | 7797.4529
2402 - Printing & Stationery: | C013 - Projects Blantyre | D614 - ACEPHEM | 2546000 | 0 | 1468.4226
2405 - Meetings: | C013 - Projects Blantyre | D614 - ACEPHEM | 27202290 | 0 | 15689.1034
2406 - Phone and Internet costs | C013 - Projects Blantyre | D614 - ACEPHEM | 12022939.12 | 0 | 6934.3109
2408 - Lab Supplies | C013 - Projects Blantyre | D614 - ACEPHEM | 2048940 | 0 | 1181.7399
2409 - Office Supplies | C013 - Projects Blantyre | D614 - ACEPHEM | 250000 | 0 | 144.1892
2500 - Electricity and Gas | C013 - Projects Blantyre | D614 - ACEPHEM | 400000 | 0 | 230.7027
2501 - Water: | C013 - Projects Blantyre | D614 - ACEPHEM | 200000 | 0 | 115.3513
2504 - Maintenance & Repairs- Motor Vehicle,Motor Cycle,Bicycles | C013 - Projects Blantyre | D614 - ACEPHEM | 19065854.51 | 0 | 10996.3596
2608 - Postgraduate Programmes:Fellowship Costs | C013 - Projects Blantyre | D614 - ACEPHEM | 0 | 2430965.79 | 0 | 1402.0758
2610 - Fuels & Oils: | C013 - Projects Blantyre | D614 - ACEPHEM | 12595902 | 0 | 7264.7711
2612 - Subsistence Allowances: | C013 - Projects Blantyre | D614 - ACEPHEM | 20477000 | 0 | 11810.2473
2615 - International Travel | C013 - Projects Blantyre | D614 - ACEPHEM | 34827199.95 | 0 | 20086.8215
2616 - Hiring expense | C013 - Projects Blantyre | D614 - ACEPHEM | 3263000 | 0 | 1881.9572
2714 - Professional Subscriptions | C013 - Projects Blantyre | D614 - ACEPHEM | 1258450.89 | 0 | 725.82
2730 - Bank & Finance Charges: | C013 - Projects Blantyre | D614 - ACEPHEM | 578518.11 | 0 | 333.6642
2741 - PPDA Levy Expense | C013 - Projects Blantyre | D614 - ACEPHEM | 45841.5 | 0 | 26.4394
2742 - Research Admin Expense | C013 - Projects Blantyre | D614 - ACEPHEM | 24287532.81 | 0 | 14007.9977
3003 - Special Expenses - Office Equipment: | C013 - Projects Blantyre | D614 - ACEPHEM | 5375999.79 | 0 | 3100.644
3005 - Special Expenses - Computers: | C013 - Projects Blantyre | D614 - ACEPHEM | 11841975 | 0 | 6829.9386
4000 - Depreciation Charge - Buildings: | C013 - Projects Blantyre | D614 - ACEPHEM | 11283100.83 | 0 | 6507.6042 |  | 230909.5145
5010 - Land | C013 - Projects Blantyre | D614 - ACEPHEM | 168120000 | 0 | 96964.3391
5011 - Buildings: | C013 - Projects Blantyre | D614 - ACEPHEM | 499324033.07 | 0 | 287988.4895
5012 - Furniture & Fittings: | C013 - Projects Blantyre | D614 - ACEPHEM | 5767375 | 0 | 3326.3723
5013 - Office Equipment: | C013 - Projects Blantyre | D614 - ACEPHEM | 35001241.38 | 0 | 20187.201
5014 - Motor Vehicle | C013 - Projects Blantyre | D614 - ACEPHEM | 145248552.71 | 0 | 83773.0782
5015 - Computers | C013 - Projects Blantyre | D614 - ACEPHEM | 24428150.12 | 0 | 14089.0996
5016 - Laboratory Equipment: | C013 - Projects Blantyre | D614 - ACEPHEM | 11829000 | 0 | 6822.4552
5100 - Accum Dpn Buildings: | C013 - Projects Blantyre | D614 - ACEPHEM | 0 | 73097955.58 |  | 42159.7368
5101 - Accum Dpn Furniture & Fittings: | C013 - Projects Blantyre | D614 - ACEPHEM | 0 | 5767375 |  | 3326.3723
5102 - Accum Dpn Office Equipment: | C013 - Projects Blantyre | D614 - ACEPHEM | 0 | 28649210.18 |  | 16523.6244
5103 - Accum Dpn Motor Vehicle | C013 - Projects Blantyre | D614 - ACEPHEM | 0 | 120708400.96 |  | 69619.3809
5104 - Accum Dpn Computers: | C013 - Projects Blantyre | D614 - ACEPHEM | 0 | 18332055.08 |  | 10573.1359
5105 - Accum Dpn Laboratory Equipment: | C013 - Projects Blantyre | D614 - ACEPHEM | 0 | 11829000 |  | 6822.4552
5300 - Debtors Control : Blantyre Campus | C013 - Projects Blantyre | D614 - ACEPHEM | 0 | 29362907.86 |  | 16935.2543
5550 - Cash Imprest: | C013 - Projects Blantyre | D614 - ACEPHEM | 25409510 | 0 | 14655.1055
5700 - Petty Cash | C013 - Projects Blantyre | D614 - ACEPHEM | 884296 | 0 | 510.0237
5907 - KUHeS Lilongwe David Livingstone Clinic- A/C 2174367 | C013 - Projects Blantyre | D614 - ACEPHEM | 0 | 7472299.71 |  | 4309.699
6075 - Small Grants Project FCDA USD - 230397021 | C013 - Projects Blantyre | D614 - ACEPHEM | 1014292.48 | 0 | 585
6118 - African Centre for Public Health and Herbal Medicine FCDA - | C013 - Projects Blantyre | D614 - ACEPHEM | 1743061173.06 | 0 | 1005322.2378
6119 - African Centre for Public Health and Herbal Medicine Local - | C013 - Projects Blantyre | D614 - ACEPHEM | 0 | 130722592.46 |  | 75395.1331
7000 - Trade Creditors Control: Blantyre Campus | C013 - Projects Blantyre | D614 - ACEPHEM | 0 | 7901051 |  | 4556.9842
7001 - Trade Creditors Control-Lilongwe Campus | C013 - Projects Blantyre | D614 - ACEPHEM | 7472299.71 | 0 | 4309.699
7006 - Trade Creditors Contol-BT Projects | C013 - Projects Blantyre | D614 - ACEPHEM | 73799059 | 0 | 42564.1029
7029 - Salaries Clearing BT Projects | C013 - Projects Blantyre | D614 - ACEPHEM | 33226015.64 | 0 | 19163.3277
7202 - WHT Tax Payable | C013 - Projects Blantyre | D614 - ACEPHEM | 0 | 13208788.22 |  | 7618.2573
7204 - OUTPUT VAT Payable | C013 - Projects Blantyre | D614 - ACEPHEM | 0 | 1580992.89 |  | 911.8483
7869 - INSURANCE PREMIUM RECOVERIES PROJECTS ACC | C013 - Projects Blantyre | D614 - ACEPHEM | 0 | 3639107.84 |  | 2098.8799
7883 - ICARTA PROJECT | C013 - Projects Blantyre | D614 - ACEPHEM | 3518300 | 0 | 2029.2032
9100 - Capital Funds: | C013 - Projects Blantyre | D614 - ACEPHEM | 0 | 464772571.03 |  | 268060.7017
9110 - General Fund/Retained Earnings: | C013 - Projects Blantyre | D614 - ACEPHEM | 0 | 407591811.68 |  | 235081.3147
9120 - Revaluation Reserves: | C013 - Projects Blantyre | D614 - ACEPHEM | 0 | 177844885.28 |  | 102573.232
Total : |  |  | 3180892869.56 | 3180892869.56 | 1834601.325 | 1834601.325 | 735723.7247
Net Income (Loss) for this list: |  |  |  | 0
803845.75